TravelTourUp

Module-wise Roadmap & Timeline

Project Delivery Plan — Confidential

Prepared: 9 April 2026

Version 1.0  |  1 Full-stack Developer (solo baseline)

# Assumptions

- Timeline is based on one full-time full-stack developer unless noted.

- Calendar weeks are indicative — adjust for team size and vendor (Duffel / car API) approvals.

- Phases are sequential at the top level; modules within a phase overlap where noted.

# Current Position (Codebase Snapshot)

A quick health-check of what exists today before estimating remaining work.

| Area | Status |
| --- | --- |
| Next.js app structure | Strong — booking routes (flights, hotels, cars), marketing, auth, admin shell all present |
| Duffel flights | Advanced — search, checkout, seat maps / bags paths in code; need E2E tightening, webhooks, refunds |
| Duffel stays (hotels) | In progress — needs complete book + pay parity with flights |
| Marketing / CMS | Substantial — Home, About, Blog, Contact, Privacy, Terms, FAQs pages present |
| Admin panel | Scaffold — users, roles, blogs, bookings, vertical lists exist; needs full ops + PDFs |
| Auth & customer account | Partial — login/signup/profile/bookings exist; wishlists, reviews, wallet, refunds need depth |
| i18n / multi-currency | Limited — display formatting only; needs systematic locale + FX strategy |
| Cars (third-party) | UI + mock flows — need real B2B car API integration end-to-end |
| Database backups | Not implemented — operational rollout needed |

# Phase A — Web MVP Completion (~2 Months Remaining)

Goal: finish all core modules and reach production-ready state.

| # | Module | Scope | Est. | Notes |
| --- | --- | --- | --- | --- |
| A1 | Duffel Flights & Stays | Search → offer → seats/bags → pay → confirm; order sync; cancellations/refunds; admin visibility | 3–4 wks | Hotels after flight path stable |
| A2 | Marketing & Trust Pages | Home sections polish, About, Blog CRUD + SEO, Contact, Privacy, Terms | 1–1.5 wks | Much already routed |
| A3 | Cars (Third-party API) | Partner search → book → pay → ticket/receipt; admin hooks | 2–3 wks | Start provider onboarding in parallel with A1 |
| A4 | Customer Account | Auth hardening, profile, My Bookings, My Reviews, Wishlists, Returns/Refunds UX + APIs, Wallet (credit/debit) | 3–4 wks | Runs parallel from week 2 |
| A5 | Language & Currency | Locale switch, translated UI (phased), currency display + checkout rules across verticals | 1.5–2 wks | Ship EN + PKR/USD first |
| A6 | Admin Panel | RBAC, users/customers, 3 verticals: booking + payment ops, PDF tickets/vouchers, refunds/credits, blog CMS, audit logs | 3–5 wks | Heaviest; stagger by vertical |
| A7 | Database Backups | Automated snapshots, retention, restore drill, off-site copy, runbook | 3–5 days | DevOps block near end |

Recommended Car API Partners (OTA-grade, B2B):

- CarTrawler — widely used behind airlines and OTAs globally.

- Booking.com / Rentalcars.com Connectivity — Booking Holdings ecosystem, strong coverage.

- Amadeus Car Rental APIs — single enterprise air + car story if Amadeus is already in stack.

  - Selection criteria: Pakistan pickup coverage, commercial terms, sandbox quality.

# Phase B — Production Go-live & Stabilization

| # | Module | Scope | Est. |
| --- | --- | --- | --- |
| B1 | Prod Cutover | Environment separation, secrets, rate limits, monitoring, alerts | 1 wk (parallel) |
| B2 | UAT & Bugfix | Real payment tests (test → pilot live), load smoke, fix P0/P1 only | 2–4 wks |

Rule: no new major modules until P0 clear and payment/booking happy-path is stable.

# Phase C — Mobile App (React Native, Same Backend)

Cross-platform app with full feature parity except admin panel.

| # | Module | Scope | Est. (1 senior RN dev) |
| --- | --- | --- | --- |
| C1 | Foundation | RN repo, envs, auth, navigation, API client parity, error/empty states | 3–4 wks |
| C2 | Flights + Stays + Cars | Search, checkout, pay, bookings, seats/bags — full parity with web | 8–12 wks |
| C3 | Account & Growth | Profile, wishlist, reviews, wallet/refunds, push notifications (optional) | 3–5 wks |
| C4 | i18n / Currency | Match web locale + currency strategy | 2 wks (overlap) |

Total mobile (feature-complete RC): ~4–6 calendar months (1 track); shorter with 2 devs + frozen APIs.

# Phase D — Mobile Store Production (iOS + Android)

| # | Step | Est. |
| --- | --- | --- |
| D1 | Compliance (privacy, ATT if needed, payments), store listings, screenshots | 1–2 wks |
| D2 | TestFlight + Play internal/open testing, device matrix | 1–2 wks |
| D3 | Review cycles + production release | 1–2 wks |

Typical: 3–5 weeks after RC, depending on review feedback.

# Phase E — Advanced Features (Web & Mobile)

Post-launch feature roadmap — sequence by revenue impact.

| ID | Module | Scope | Est. |
| --- | --- | --- | --- |
| E1 | Flight + Hotel Bundles | Cached bundle pricing rules, combined checkout UX, failure rollback | 6–10 wks |
| E2 | Cross-sell: Flights ↔ Hotels | Post-flight hotel suggestions, same-trip attach (Duffel-only first) | 4–8 wks |
| E3 | Packages | Named packages, margins, inventory rules, CMS merchandising | 6–10 wks |
| E4 | Advance Purchase Pricing | Fare rules, calendars, 'cheapest window' UX, caching, disclaimers | 6–12 wks |
| E5 | Agent Portal (optional) | Agent RBAC, book on behalf, commission, payout cycles | 10–16 wks |

Competitive Parity Ideas (backlog — prioritize 2–3 per half-year):

- Genius / loyalty tiers & price alerts

- Flexible dates search & trip planner

- Post-booking concierge chat & travel insurance

- Affiliate / referral program

- Buy Now Pay Later (regional providers)

- Corporate travel lite

# High-level Timeline Overview

| Phase | Duration | Period (approx.) |
| --- | --- | --- |
| A — Web MVP completion | ~2 months | Now → end of Month 3 |
| B — Production & stabilization | ~1 month | Month 4 |
| C — React Native mobile app | ~4–6 months | Month 4 → Month 9 |
| D — Store production | ~1 month | Month 9 → Month 10 |
| E — Advanced features | Ongoing (phased) | Month 10+ |

—

Document version 1.0 — aligned with repository snapshot and stated 3-month Phase 1.

Timelines assume solo developer baseline. Scale down proportionally with additional team members.